## Issues Report
Title | Description | Issue ID | URL | State | Assignee | Created At | Due Date | Milestone | Labels | Functions/Screens
Implement Multiple Voucher System | Backend logic in CheckoutServlet to process Merchant and Platform vouchers together. | 1 | https://github.com/hung2101-fushiguro/ClickEat/issues/1 | Closed | Đạt | 2026-03-20 | 2026-03-27 | Sprint 3 | Feature, Done | Checkout
UI for Multiple Vouchers | Update checkout.jsp to include checkbox-based voucher selection. | 2 | https://github.com/hung2101-fushiguro/ClickEat/issues/2 | Closed | Bảo | 2026-03-21 | 2026-03-27 | Sprint 3 | Feature, Done | Checkout
Configure OpenAI API Integration | Integrate OpenAI API in AIChatServlet as primary chat provider with Gemini fallback. | 3 | https://github.com/hung2101-fushiguro/ClickEat/issues/3 | Closed | Hưng | 2026-03-24 | 2026-03-26 | Sprint 3 | Feature, Done | AI Chat
Fix CartItem Model-JSP Mismatches | Include name and imageUrl fields in CartItem model and DAO. | 4 | https://github.com/hung2101-fushiguro/ClickEat/issues/4 | Closed | Đạt | 2026-03-17 | 2026-03-18 | Sprint 2 | Bug, Done | Cart
Merchant Wallet Balance Zero Bug | Investigate and fix issue where wallet balance shows zero due to OrderDAO not updating it upon delivery. | 5 | https://github.com/hung2101-fushiguro/ClickEat/issues/5 | Closed | Bảo | 2026-03-17 | 2026-03-18 | Sprint 2 | Bug, Done | Merchant Wallet
Update E2E Test Suite Data | Modify test fixtures to align with SQL seed files and enable headless mode. | 6 | https://github.com/hung2101-fushiguro/ClickEat/issues/6 | Closed | Hưng | 2026-03-12 | 2026-03-13 | Sprint 1 | Task, Done | Testing
Populate Excel Documentation Templates | Fill test data and worksheets for project documentation templates. | 7 | https://github.com/hung2101-fushiguro/ClickEat/issues/7 | Closed | Hưng | 2026-03-18 | 2026-03-19 | Sprint 2 | Task, Done | Docs
Optimize Image Rendering | Add CSS-based fallbacks for missing images in product listings. | 8 | https://github.com/hung2101-fushiguro/ClickEat/issues/8 | Closed | Bảo | 2026-03-15 | 2026-03-16 | Sprint 2 | Task, Done | Product List
Payment Gateway Integration | Integrate VNPay for cashless payment options in checkout. | 10 | https://github.com/hung2101-fushiguro/ClickEat/issues/10 | Open | Đạt | 2026-03-27 | 2026-04-05 | Sprint 4 | Feature, Doing | Checkout